## Slide 1: Housing Replacement Analysis Project
Project Kick-off Meeting
October 31, 2011
Prepared by Jonathan Magsino

## Slide 2: Agenda
Project Overview
Project Phases
  Discovery Phase
  Define Phase
  Design Phase
Business Justification / Project Scope
Business Process - Meetings
Project Roles
Review and Sign-off Responsibilities
Communication Plan
Success Criteria
Timelines / Milestones
Next Steps

## Slide 3: Project Overview
The project will focus on getting a clear understanding of DSL Housing:
    Current State
      What are the processes and functions of DSL Housing today?
      How is CBORD’s Odyssey HMS being utilized to support this?
    Future State
      What is the vision?
How will we get from the current to future state?
  Discovery
  Define
  Design

## Slide 4: Discovery Phase
Approach
  During Discovery, we will document current DSL Housing processes. We will work with DSL Housing resources to
    Map each step within the housing lifecycle.
    Determine providers and consumers of housing data.
    Understand security protocols around housing data.
    Identify all stakeholders of the DSL Housing lifecycle.
Deliverable
  Baseline assessment of DSL current Housing environment.
  Detailed diagrams of DSL Housing current processes.

## Slide 5: Define Phase
Approach
  With Discovery completed, we can Define what will occur when CBORD’s Odyssey HMS transforms into the system of record for DSL Housing and integrates with other systems of MIT
  Working with DSL Housing resources, we can Define:
    Changes to improve the housing lifecycle
    Ways to reduce the effort to maintain housing
    Utilization of IS&T supported security protocols (certificates / roles database) around access and data
    Requirements of all stakeholders, providers and consumers of housing data for the future (to-be) state
Deliverable
  Description of the To-Be model of DSL Housing
  Baseline and To-Be process maps of DSL Housing

## Slide 6: Design Phase
  Approach
    Now that we have completed Define, the project team needs to identify what is the least impactful way of introducing and integrating identified changes.
    We must also Define what is required of our stakeholders to reach our goal.
  Deliverable
    The Design phase will deliver a proposal from the project team to DSL Housing management and Student Systems management describing:
      How to implement required changes of DSL Housing, Student Systems, and affected departments and systems.
      The level of effort and resources required from each stakeholder
      High level project plan.

## Slide 7: Business Justification / Project Scope
To get things started, a business justification document will be delivered after this Kick-Off presentation.
Approval (sign-off) will be required by identified resources as specified in the Business Justification.
We will then collaborate on a Project Scope Document
These documents are part of IS&T Student Systems Software Development Lifecycle documentation.

## Slide 8: Business Process – Meetings
Division of Student Life / Housing / IS&T
Selected Departments
  To be determined with input from DSL Housing resources
Stakeholders
  To be determined with input from DSL Housing resources
Who should be included in the meetings?

## Slide 9: Project Roles
Sponsors
  Henry Humphreys
  Eamon Kearns
Project Team
  Housing Subject Matter Experts (SMEs)
    Adam Keyes
    Robin Baughman
  Student Systems
    Ross Runnion (Business Analyst)
    Jonathan Magsino (Project Manager)

## Slide 10: Review and Sign-off Responsibilities
Approvers (who approve the deliverable from each phase)
  Project Sponsors
  Project Team
  Student Systems Managers
  Anyone else?
Reviewers (Review deliverables and offer feedback)
  Approvers (are automatically assumed to be reviewing the deliverables)
  Stakeholders – as identified by the project team
  Anyone else?

## Slide 11: Communication Plan
What | Sponsor Meetings | Project Team Status Meetings | Approvals
Document | Sponsor Status Document | Status Report | Business Justification Project Scope
When | Monthly | Weekly (as needed) | TBD
How | In Person | In Person | Review session held. Afterwards, the project manager will request approvals of the latest versions via e-mail.
Meeting Attendees | Henry Humphreys | Adam Keyes | TBD
 | Eamon Kearns | Robin Baughman | 
 | Lori Singer | Ross Runnion | 
 | Jonathan Magsino | Jonathan Magsino | 
 | JoAnne Stevenson | Lori Singer (as needed) | 
 |  | JoAnne Stevenson (as needed) | 
Document Preparer | Jonathan Magsino | Jonathan Magsino | Ross Runnion Jonathan Magsino

## Slide 12: Timeline and Milestones
Meeting Groups
  DSL Housing and Student Systems
  Stakeholders as identified by the project team
Discovery Phase
  Starting in November
Define Phase
  TBD
Design Phase
  TBD

## Slide 13: Success Criteria
Clear, documented, and approved understanding of DSL Housing’s baseline lifecycle process (Discovery Phase)
Clear, documented, and approved understanding of DSL Housing’s To-Be (future) process (Define Phase)
Clear, documented, and approved proposal on how to implement a solution for DSL Housing with estimates from all stakeholders. (Design Phase)

## Slide 14: Next Steps
Review and Approve Business Justification and Project Scope Deliverables
Determine Stakeholders
Schedule meetings
  Review Business Justification (Ross, Adam, Robin, Jonathan)
  Review Project Scope
  Project Team Meetings
  Project Sponsor Meetings
  Meetings to gain baseline understanding of the Housing lifecycle.