## Slide 1: MALWARE PROTECTION OVERHAUL PROJECT
Project Kick-Off Meeting
December 05, 2012

## Slide 2: Agenda
Opening Remarks/Introductions
Project Overview
Background
Project Scope
Evaluation Criteria
Vendors for evaluate
Project Approach
High Level Project Timeline
Project Organization
Project Communications
Next Steps
Questions and Answers

## Slide 3: Opening Remarks / Introductions
Introductions
Sponsor comments
Team comments

## Slide 4: Project Overview
Replace IS&T’s current antivirus software solution for the Windows and Macintosh platforms
Windows products to evaluate
  Microsoft Systems Center 2012 (formerly known as Forefront)
  ESET
OS X Products to evaluate
  ESET
  Sophos
PCI machines, mobile devices and Linux are out of scope

## Slide 5: Background
IS&T offers McAfee AntiVirus (Windows & Linux) and McAfee Security Suite (Mac) as it’s malware solution
MIT users have voiced displeasure with the McAfee solution for a variety of reasons
  Sub-par system performance and
  Poor end-user support
  heavy emphasis on heavily managed and homogeneous environments
For MIT, the product has proven to be ineffective, causing problems in our academic environment and slowing adoption

## Slide 6: Project Scope
Project Scope
Team will evaluate and procure a malware protection software for the Windows platform to replace McAfee (for domain and standalone machines).
  Systems Center 2012 is the 1st preference for the Windows platform. The project team will evaluate this product first. If Systems Center 2012 does not meet MIT’s needs, the team will explore other products.
Team will evaluate and procure a malware protection software for OS X users to replace current offering (McAfee Security Suite).
Out of Scope
Mobile operating systems
Linux operating system
PCI machines will stay with McAfee for the time being
Software distribution to end users (push)

## Slide 7: Evaluation Criteria
Must Haves:
Established product (in market for > 2 years)
Intelligence gathering capabilities (Console metrics)
Low overhead (does not tax systems)
Nice to Have:
Layered Console

## Slide 8: Vendors for Evaluation
Windows
Systems Center 2012 (formerly known as Forefront)
ESET
Mac
Sophos
ESET

## Slide 9: Project Approach
Planning
Security Team Evaluation
Team Vendor Demo(s) and Evaluation
Analyze Recommendation and Solution
Checkpoint
Communications
Pilot Rollout
Checkpoint
Procurement
Documentation
Communications
Early Adopters
Checkpoint
Communications
Full Rollout

## Slide 10: High Level Project Timeline
NOV 2012 | DEC 2012 | JAN 2012 | FEB 2012 | MAR 2013 | APR 2013 | MAY 2013 | JUNE2013 | JULY 2013
Security Team – Microsoft Solution Evaluation
Pilot
Purchase
Checkpoint
Planning
Early Adopters
Full Rollout
Checkpoint
Checkpoint
Pilot
Purchase
Checkpoint
Early Adopters
Full Rollout
Checkpoint
Checkpoint
Ext Team evaluation
Analyze Solution
Security Team – MAC Solution Evaluation
Ext Team evaluation
Analyze Solution

## Slide 11: Project Organization
Sponsors:
Mark Silis, IS&T
Core team:
Andrew Munchbach
Tim McGovern
Sophie Wong
Other project support:
Mike Halsall
Monique Yeaton
David Millar
Stakeholders
Oliver Thomas
Justin Fleming
Chris Gresham
Dave Conlon
Richard Edelson
Anne Sylvester
Steve Landry
Jon Reed

## Slide 12: Project Communications
Meetings and Project Updates
  Weekly project team meeting
  Monthly sponsor meeting
  Regular project update available to project stakeholders via project wiki
  Ad hoc meetings as needed to address business, technical issues, focused topics
Project wiki site with project status, meeting summaries, and all project docs
  Wiki: https://wikis.mit.edu/confluence/display/MalwareProtection/Home

## Slide 13: Next Steps
  Project team will work to complete initial vendor evaluation and prepare for team vendor demo(s)
  Stakeholders should begin documenting questions and requirements for malware solution.

## Slide 14: Questions and Answers